## Sheet1
Date | Assign Date | Assign Time | Expected Date | Id | Module | Issues | Screenshort and Video | Status | Assign To | Bug Type | Qa By | Issue Solved By | Current Status | Bug Priority Level | Again Arise Issues Date | Dev Comment | SQA Comment | Bug Solving End Time
2025-11-02 | 2025-11-02 |  |  | 1 | Pagination | Boi Sodai pagination issues | Bugsrc | Close | Safayat Hossain | Functional | Imran | Safayat Hossain | Production | High
|  |  |  | 2 | Boisodai | Community page is not properly showing | Bugsrc | Fail |  | Functional | Imran |  | Production | High
2025-11-12 | 2025-11-12 |  |  | 3 | Search issues sub category | After searching, clicking on Bangla Academy does not perform any action | Bugsrc | Close | Safayat Hossain | Functional | Imran | Safayat Hossain | Production | High
2025-11-12 |  |  |  | 4 | Share link | Book details or title are not showing in the share link | Bugsrc | Fail |  | UI | Imran |  | Production | High
2025-11-13 |  |  |  | 4 | Order | For BVUJ and BZSV numbers, two separate orders were placed but both invoices show the same book, and searching shows only one order |  | Close |  | Functional | Imran |  | Production | High
2025-11-18 |  |  |  | 5 | Pagination | Product page pagination needs modification | Bugsrc | Close | Md. Nazmul Hasan | Other | Imran |  | Production | High
2025-11-18 |  |  |  | 6 | Pagination | Product number mismatch | Bug Video | Close | Md. Nazmul Hasan | Other | Imran |  | Production | High
|  |  |  | 7 | Order | Order duplication issues | Bugsrc | Close |  | Functional | Imran |  | Production | High
|  |  |  | 8 |  | Book is being added but takes too much time | Bugsrc | Close |  | Functional | Imran |  | Production | High
| 2025-11-22 | 2025-12-08 |  | 9 |  | Staff cannot see duplicate orders from order panel | Bug Video | Close | Safayat Hossain | Functional | Imran |  | Production | High |  |  | Bugvideo-Extra
|  | 2025-11-19 |  | 10 |  | By default no one should be assigned, need to add “All” button | Bug Video | Close |  | Functional | Imran |  | Production | High
|  |  |  | 11 |  | Unnecessary data should not be shown | Bugsrc | Close |  | UI | Imran |  | Production | High
|  |  |  | 12 |  | After link, category or author should remain as query parameter |  | Close |  | Functional | Imran |  | Production | High
2025-11-22 | 2025-11-22 |  |  | 13 | Order all count | Order total count is not properly showing | Bug video | Close | Rakib Bhai Founder | Functional | Imran |  | Production | High
|  |  |  | 14 |  | Order cannot be changed |  | Close |  | Functional | Imran |  | Production | High
|  |  |  | 15 |  | Order shipping charge cannot be changed |  | Close |  | Functional | Imran |  | Production | High
|  |  |  | 16 |  | Order discount cannot be created |  | Close |  | Functional | Imran |  | Production | High
| 2025-12-09 |  |  | 17 |  | Address change note issue |  | Close | Safayat Hossain | Functional | Imran |  | Production | High |  |  | Invoice note and other site id
|  |  |  | 18 |  | Sidebar does not close properly | Bugsrc | Close |  | Functional | Imran |  | Production | High
|  |  |  | 19 |  | Search bar is missing | Bugsrc | Close | Md. Nazmul Hasan | Functional | Imran |  | Production | High
|  |  |  | 20 |  | Supplier and author are not working |  | Close |  | Functional | Imran |  | Production | High
2025-11-23 | 2025-11-24 |  |  | 21 |  | Book priced 130 is ordered at 220, price and address are not updating | Bugsrc | Close | Safayat Hossain | Functional | Imran |  | Production | Urgent
|  |  |  | 22 |  | Searching issues |  | Close |  | Functional | Imran |  | Production | Urgent
|  |  |  | 23 |  | User account category does not work under staff but works in admin | Bug video | Close |  | Functional | Imran |  | Production | Urgent
| 2025-11-23 |  |  | 24 |  | Category filter is not working | Bugsrc | Close | Rakib Bhai Founder | Functional | Imran |  | Production | Urgent
| 2025-11-23 |  |  | 25 |  | Report page shows 404 error |  | Close | Rakib Bhai Founder | Functional | Imran |  | Production | Urgent
2025-11-24 |  |  |  | 26 |  | Cost price miscalculation | Bugsrc | Close |  | Functional | Imran |  | Production | Urgent
|  |  |  | 27 | Category | Category is not showing more than 64 items | Bugsrc | Close |  | Functional | Imran |  | Production | Urgent
2025-11-25 |  |  |  | 28 |  | Author list shows one less book than actual count | Bugsrc | Close |  | Functional | Imran |  | Production | Urgent |  |  | Bugsrc
|  |  |  | 29 |  | Print label text should be “Print” instead of current options | Bugsrc | Not a Bug |  | Functional | Imran |  | Production | Urgent
|  |  |  | 30 |  | Filter is not working | Bugsrc | Close | Md. Nazmul Hasan | Functional | Imran |  | Production | Urgent
|  |  |  | 31 |  | If logged in with Gmail, product view keeps loading | Bugsrc | Close | Md. Nazmul Hasan | Functional | Imran |  | Production | Urgent
|  |  |  | 32 |  | Same issue when logging in with phone number | Bugsrc | Close | Md. Nazmul Hasan | Functional | Imran |  | Production | Urgent
|  |  |  | 33 |  | Profile disappears | Bugsrc | Close | Md. Nazmul Hasan | Functional | Imran |  | Production | Urgent
|  |  |  | 34 |  | Dashboard disappears | Bugsrc | Close | Md. Nazmul Hasan | Functional | Imran |  | Production | Urgent
|  |  |  | 35 |  | Popup message cannot be closed | Bugsrc | Close | Md. Nazmul Hasan | Functional | Imran |  | Production | Urgent
2025-11-26 |  |  |  | 36 |  | Invoice data is not properly updated | Bug Video | Close | Safayat Hossain | Functional | Imran | Safayat Hossain | Production | Urgent
|  |  |  | 37 |  | Bottom scrollbar should be removed and fit into one page | Bugsrc | Close | Safayat Hossain | Functional | Imran |  | Production | High
|  |  |  | 38 |  | All functions are not working and order gets auto-assigned to one person | Bugsrc | Close |  | Functional | Imran |  | Production | Urgent |  |  | Staff account- Ac-01868427117 Pass- Mintubhai@
2025-11-27 | 2025-12-10 |  |  | 39 |  | Admin notes are visible to customers, need internal note option | Bugsrc | Close | Md. Nazmul Hasan | Functional | Imran |  | Production | Urgent
| 2025-12-09 |  |  | 40 |  | Sub-sub category URL does not change, cannot run ads |  | Close | Md. Nazmul Hasan | Functional | Imran |  | Production | Urgent
2025-12-02 |  |  |  | 41 |  | Staff search option is missing | Bug video | Close | Md. Ashikuzzaman | Functional | Imran |  | Production | Client Urgent
| 2025-12-08 |  |  | 42 |  | Product page author and supplier issues | Bug video | Close | Md. Ashikuzzaman | Functional | Imran |  | Production | Client Urgent
2025-12-03 | 2025-12-08 |  |  | 43 |  | Pick list shows only 9 products everywhere and report quantity mismatch | Bug Video | Fail | Mir Nayem | Functional | Imran |  | Production | Medium
2025-12-06 | 2025-12-07 |  |  | 44 |  | Category query types and bulk price not working | Bug video | Close | Md. Nazmul Hasan, Rakibul Islam, Mir Nayem | Functional | Imran |  | Production | Client Urgent |  | apis issue
| 2025-12-17 |  |  | 45 |  | Pagination needs to be added in category, subcategory, and child category | Bugsrc | Close | Safayat Hossain | Functional | Imran |  | Production | High
| 2026-02-18 |  |  | 46 |  | Website category, publisher, author homepage issues | Bug Video | Resolved | Rakibul Islam, Morshedul Islam Munna | Functional | Imran |  | Production | Client Urgent |  | Need to be add backend features | backend r jonno relation make korte hobe
| 2025-12-08 |  |  | 47 |  | Staff account features not working | Bug Src | Close | Md. Nazmul Hasan | Functional | Imran |  | Production | Client Urgent
|  |  |  | 48 |  | Supplier search issue | Bug Video | Close | Md. Nazmul Hasan | Functional | Imran |  | Production | Client Urgent
2025-12-07 |  |  |  | 49 |  | Product short details are blank (supplier related issue) | Bugsrc | Close | Md. Nazmul Hasan | Functional | Imran |  | Production | Client Urgent
| 2025-12-17 |  |  | 50 |  | Product spacing issue | Bugsrc | Close | Mir Nayem | Functional | Imran |  | Production | Low
| 2025-12-08 |  |  | 51 |  | Shipment missing in staff account | Bugsrc | Close | Rakibul Islam | Functional | Imran |  | Production | High |  | In order route missing Shipment need to add here
2025-12-08 | 2025-12-08 |  |  | 52 |  | Remove duplicate sorting in author |  | Close | Md. Ashikuzzaman | Functional | Imran |  | Production | High
| 2025-12-08 |  |  | 53 |  | Cancel order suggestion update reason missing | Bugsrc | Close | Safayat Hossain | Functional | Imran |  | Production | High
| 2025-12-08 |  |  | 54 |  | First time dashboard redirect issue |  | Not a Bug | Rakibul Islam | Functional | Imran |  | Production | Medium |  | This is a not issue rather it's a logic
2025-12-08 | 2025-12-08 |  |  | 55 |  | Category query type lowest/highest price not working |  | Close | Morshedul Islam Munna | Functional | Imran |  | Production | Client Urgent |  |  | All backend depenedency
| 2025-12-09 |  |  | 56 |  | Product report data mismatch despite same date filter | Bugsrc | Close | Safayat Hossain | Functional | Imran |  | Production | Urgent |  |  | backend issues
2025-12-10 | 2025-12-10 |  |  | 57 |  | Need schema/tree for category, publisher, author on homepage | Bugsrc | Fail | Safayat Hossain | Functional | Imran |  | Production | High
| 2025-12-10 |  |  | 58 |  | Inventory sorting issue | Bugsrc | Close | Safayat Hossain | Functional | Imran |  | Production | Client Urgent
2025-12-11 | 2025-12-17 |  |  | 59 |  | Reseller data mismatch |  | Close | Rakibul Islam | Functional | Imran |  | Production | High
| 2025-12-11 |  |  | 60 |  | Inventory search and sorting not working | Bugsrc | Close | Mir Nayem | Functional | Imran |  | Production | High |  |  | Store-Issue-URL
| 2025-12-11 |  |  | 61 |  | Voucher validation (once per customer, max discount) not saved properly | Bug Video | Close | Rakibul Islam | Functional | Imran |  | Production | High |  |  | Sorting is not working (backend issues)
| 2025-12-11 |  |  | 62 |  | Campaign save shows error | Bugsrc | Close | Rakibul Islam | Functional | Imran |  | Production | High
| 2024-12-13 |  |  | 63 |  | Inactive suppliers are showing in supplier list | Bugsrc | Not a Bug | Rakibul Islam | Functional | Imran |  | Production | High
2025-12-14 | 2025-12-14 |  |  | 64 |  | Storefront sorting not working | Bug Video | Close | Safayat Hossain | Functional | Imran |  | Production | High
|  |  |  | 65 |  | Search issues in category, supplier, author, brand across all pages | Bugsrc | Not a Bug | Md. Nazmul Hasan | Functional | Imran |  | Production | High |  |  | Third party api issues
|  |  |  | 66 |  | Order with 32 books shows only 10 |  | Close |  | Functional | Imran |  | Production | High
| 2025-12-15 |  |  | 67 |  | Order is placed based on printed price incorrectly | Bugsrc | Close | Safayat Hossain, Morshedul Islam Munna | Functional | Imran |  | Production | Client Urgent
|  |  |  | 68 |  | Product searching issues |  | Close |  | Functional | Imran |  | Production | Low |  |  | Rokomari URL
2025-12-17 |  |  |  | 69 |  | Delivery ratio not working | Bugsrc | Close | Safayat Hossain | Functional | Imran |  | Production | Client Urgent
| 2026-02-18 |  |  | 70 |  | Inactive products appear in storefront search | Bugsrc | Close |  | Functional | Imran |  | Production | Client Urgent
|  |  |  | 71 |  | Subcategory and sub-subcategory are not clickable | Bugsrc | Close | Safayat Hossain | Functional | Imran |  | Production | Client Urgent
2025-12-21 | 2025-12-22 |  |  | 72 | Order activity | Multiple category and sub-subcategory feature needs to be added | Bugsrc | Close | Safayat Hossain | Functional | Imran |  | Production | Client Urgent |  |  | Discussion Video
| 2025-12-22 |  |  | 73 |  | Timezone mismatch issues | Bugsrc | Close | Safayat Hossain | Functional | Imran |  | Production | Client Urgent
| 2025-12-22 |  |  | 74 |  | Selecting subcategory should show related author and publisher | Bugsrc | Close | Safayat Hossain | Functional | Imran |  | Production | Client Urgent
| 2025-12-22 |  |  | 75 |  | Flash time update missing | Bugsrc | Close | Safayat Hossain | Functional | Imran |  | Production | Client Urgent
| 2025-12-22 |  |  | 76 |  | Time sequence logic needs correction | Bugsrc | Not a Bug | Safayat Hossain | Functional | Imran |  | Production | Client Urgent
|  |  |  | 77 |  | Staff actions should show staff, admin actions should show admin |  | Close | Md. Nazmul Hasan | Functional | Imran |  | Production | High
2025-12-22 | 2025-12-22 |  |  | 78 |  | Order process sequence needs fixing | Bugsrc | Close | Mir Nayem | Functional | Imran |  | Production | High
|  |  |  | 79 |  | Order communication should not be visible to customer | Bugsrc | Backend/APIs issue | Safayat Hossain, Morshedul Islam Munna , Rakib Bhai Founder | Functional | Imran |  | Production | High
|  |  |  | 80 |  | Staff name and number showing incorrectly in order activity | Bugsrc | Fail |  | Functional | Imran |  | Production | High
2025-12-27 |  |  |  | 81 |  | Boi Sodai mobile responsiveness issues |  | Close | Safayat Hossain | Functional | Imran |  | Production | High
2025-12-28 | 2025-12-28 |  |  | 82 |  | Add query in child and sub-sub category |  | Close | Safayat Hossain | Functional | Imran |  | Production | High
2025-12-28 |  |  |  | 83 |  | Order placed with printed price issue |  | Fail |  | Functional | Imran |  | Production | Medium
2025-12-28 |  |  |  | 84 |  | Logistics note not syncing to courier system | Bug video | Close | Safayat Hossain | Functional | Imran |  | Production | High
2025-12-28 | 2025-12-28 |  |  | 85 |  | Logistics note not saved in order details |  | Close | Rakib Bhai Founder, Morshedul Islam Munna | Functional | Imran |  | Production | Client Urgent
|  |  |  | 86 |  | Review and rating submission issue |  | Close | Md. Nazmul Hasan | Functional | Imran |  | Production | Client Urgent
2025-12-29 | 2026-02-18 |  |  | 87 |  | #ERROR! | Bugsrc | Close |  | Functional | Imran |  | Production | Client Urgent |  |  | Discussion video
2025-12-30 |  |  |  | 88 |  | Author list does not show all books | Bugsrc | Fail |  | Functional | Imran |  | Production | Low
|  |  |  | 89 |  | Purchase click registers multiple times | Bugsrc | Fail | Morshedul Islam Munna | Functional | Imran |  | Production | Client Urgent
2026-01-03 | 2026-01-03 |  |  | 90 |  | Category search issues |  | Close | Rakib Bhai Founder, Safayat Hossain | Functional | Imran |  | Production | Client Urgent
| 2026-01-03 |  |  | 91 |  | Homepage should show books by subcategory and child category in separate rows |  | Close | Morshedul Islam Munna | Functional | Imran |  | Production | Client Urgent
2026-01-04 | 2026-01-04 |  |  | 92 |  | Add remove option in wishlist |  | Close | Safayat Hossain | Functional | Imran |  | Production | Client Urgent
2026-01-05 | 2026-01-05 |  |  | 93 |  | Staff report data mismatch | Bugsrc | Close | Md. Nazmul Hasan | Functional | Imran |  | Production | Client Urgent
|  |  |  | 94 |  | Extra payment charge showing |  | Close | Safayat Hossain, Mir Nayem | Functional | Imran |  | Production | Client Urgent
|  |  |  | 95 |  | Product view behaves incorrectly when accessed via ad or referral link |  | Close | Morshedul Islam Munna | Functional | Imran |  | Production | Client Urgent
2026-01-06 | 2026-01-06 |  |  | 96 |  | Invoice paid sticker opacity too high | Bugsrc | Close | Mir Nayem | Functional | Imran |  | Production | Client Urgent | Again Arise ( 01-21-2026)
| 2026-01-06 |  |  | 97 |  | Product page reload issues |  | Close | Mir Nayem | Functional | Imran |  | Production | Client Urgent | Again Arise ( 01-21-2026)
| 2026-01-06 |  |  | 98 |  | Individual product review not working | Bugsrc | Close | Mir Nayem | Functional | Imran |  | Production | Client Urgent | Again Arise ( 01-21-2026)
| 2026-01-06 |  |  | 99 |  | Purchase order list not showing | Bugsrc | Close | Mir Nayem | Functional | Imran |  | Production | Client Urgent | Again Arise ( 01-21-2026)
| 2026-01-06 |  |  | 100 |  | Order saving validation issues | Bugsrc | Close | Md. Ashikuzzaman | Functional | Imran |  | Production | Medium
| 2026-01-06 |  |  | 101 | Invoice Deliver Method | Purchase and checklist quantity mismatch | Bugsrc | Close | Md. Ashikuzzaman | Functional | Imran |  | Production | Client Urgent | Again Arise ( 01-11-2026)
2026-01-07 | 2026-01-11 |  |  | 102 |  | Stock out product still accepting orders | Bugsrc | Close | Safayat Hossain, Morshedul Islam Munna | Functional | Imran |  | Production | Client Urgent
| 2026-01-07 |  |  | 103 |  | Print label naming issue | Bugsrc | Close | Md. Ashikuzzaman | Functional | Imran |  | Production | Client Urgent
| 2026-01-20 |  |  | 104 |  | Payment method mismatch showing paid but no history | Bugsrc | Resolved | Safayat Hossain | Functional | Imran |  | Production | Client Urgent |  |  | Rokomari Site URL (Backend Api Done)
2026-01-10 | 2026-01-10 |  |  | 105 |  | Add supplier name in print invoice |  | Close |  | Functional | Imran |  | Production | Client Urgent
| 2026-01-10 |  |  | 106 |  | Request quote feature needed for corporate orders | Bug video | Close | Safayat Hossain | Functional | Imran |  | Production | Client Urgent
| 2026-01-10 |  |  | 107 |  | Customer payment going to wrong merchant | Bugsrc | Fail | Safayat Hossain | Functional | Imran |  | Production | Client Urgent
2026-01-12 | 2026-01-12 |  |  | 108 |  | Collection page redirect issues | Bugsrc | Resolved | Safayat Hossain | Functional | Imran |  | Production | Client Urgent |  |  | Product URL Link
2026-01-11 |  |  |  | 109 |  | Category and subcategory link working in reverse | Bugsrc | Fail |  | Functional | Imran |  | Production | Client Urgent
| 2026-01-11 |  |  | 110 |  | Deleted books still showing in backend |  | Resolved | Md. Ashikuzzaman | Functional | Imran |  | Production | Client Urgent
| 2026-01-11 |  |  | 110 |  | Slug naming issues affecting authors and publishers | Bugsrc | Resolved | Md. Ashikuzzaman | Functional | Imran |  | Production | Client Urgent
2026-01-12 | 2026-01-12 |  |  | 111 |  | Round figure needed in frontend and backend | Bugsrc | Fail | Morshedul Islam Munna | Functional | Imran |  | Production | Urgent
|  |  |  | 112 |  | Paid logo not showing | Bugsrc | Resolved | Md. Nazmul Hasan | Functional | Imran |  | Production | Urgent |  | issue palaiche | local url link
|  |  |  | 113 |  | Publisher click not working after search | Bugsrc | Fail |  | Functional | Imran |  | Production | Urgent
|  |  |  | 114 |  | Publisher and author not remaining selected |  | Inprogress |  | Functional | Imran |  | Production | Urgent
|  |  |  | 115 |  | Negative product price showing |  | Inprogress |  | Functional | Imran |  | Production | Urgent
|  |  |  | 116 |  | Organic order listing needed by author, category, subcategory, publisher |  | Inprogress |  | Functional | Imran |  | Production | Urgent
|  |  |  | 117 |  | Buy all together feature |  | Inprogress |  | Functional | Imran |  | Production | Urgent
|  |  |  | 118 |  | Show more should be inside sidebar |  | Inprogress |  | Functional | Imran |  | Production | Urgent
|  |  |  | 119 |  | Latest books sold section |  | Inprogress |  | Functional | Imran |  | Production | Urgent
|  |  |  | 120 |  | Customer also bought section |  | Inprogress |  | Functional | Imran |  | Production | Urgent
|  |  |  | 121 |  | Add to cart popup should show customer bought |  | Inprogress |  | Functional | Imran |  | Production | Urgent
|  |  |  | 122 |  | Multisearch should send slug instead of unicode |  | Inprogress |  | Functional | Imran |  | Production | Urgent
|  |  |  | 123 |  | Admin product search not working |  | Need to new feature |  | Functional | Imran |  | Production | Urgent
2026-01-14 | 2026-01-14 |  |  | 124 |  | Voucher usage count not working | Bugsrc | Close | Safayat Hossain, Morshedul Islam Munna, Md. Nazmul Hasan | Functional | Imran |  | Production | Client Urgent
| 2026-01-14 |  |  | 125 |  | Promo code product search by author not working | Bugsrc | Backend/APIs issue | Rakibul Islam | Functional | Imran |  | Production | Client Urgent | Backend calculations issue
| 2026-01-14 |  |  | 126 |  | Gift wrap option needed in checkout | Bugvideo | Close | Rakibul Islam | Functional | Imran |  | Production | Client Urgent
|  |  |  | 127 |  | Payment done but no payment sticker | Bugsrc | Need to new feature
2026-01-15 | 01-15-2026 and 01-17-2026 |  |  | 128 |  | Invoice supplier/quantity mismatch | Bugsrc | Reopen | Safayat Hossain | Functional | Imran |  | Production | Client Urgent
| 2026-01-15 |  |  | 129 |  | Cannot create promo code |  | Close | Rakibul Islam | Functional | Imran |  | Production | Client Urgent
| 2026-01-15 |  |  | 130 |  | Voucher pagination needed |  | Close | Rakibul Islam | Functional | Imran |  | Production | Client Urgent
| 01-15-2026 and 01-17-2025 |  |  | 131 |  | Product cover upload quality issue |  | Close | Rakibul Islam | Functional | Imran |  | Production | Client Urgent
2026-01-17 | 2026-01-17 |  |  | 132 |  | Recently sold frontend issue |  | Close | Md. Nazmul Hasan | Functional | Imran |  | Production | Client Urgent
2026-01-18 | 2026-01-18 |  |  | 133 |  | Order method shows online payment instead of COD |  | Not a Bug |  | Functional | Imran |  | Production | Client Urgent
2026-01-19 | 2026-01-19 |  |  | 134 |  | Category URL naming issues |  | Inprogress | Md. Ashikuzzaman | Functional | Imran |  | Production | Client Urgent
2026-01-20 | 2026-01-20 |  |  | 135 |  | Book name appears incorrectly in subcategory URL |  | Not a Bug | Md. Ashikuzzaman | Functional | Imran |  | Production | Client Urgent
2026-01-24 | 2026-01-24 |  |  | 136 |  | Subcategory not passing initially | Bug Video | Resolved |  | Functional | Imran |  | Production | Client Urgent
| 2026-01-24 |  |  | 137 |  | Subcategory details and filters issue |  | Resolved | Md. Nazmul Hasan | Functional | Imran |  | Production | Client Urgent
| 2026-01-24 |  |  | 138 |  | Child category search issue in backend |  | Resolved | Md. Nazmul Hasan | Functional | Imran |  | Production | Client Urgent
|  |  |  | 139 |  | Publisher URL shows undefined |  | Resolved | Md. Nazmul Hasan | Functional | Imran |  | Production | Client Urgent
|  |  |  | 140 |  | Supplier toggle not working and product not showing in client side |  | Backend/APIs issue |  | Functional | Imran |  | Production | Client Urgent
| 2026-01-24 |  |  | 141 |  | Sub-subcategory homepage query not working |  | Resolved | Md. Nazmul Hasan | Functional | Imran |  | Production | Client Urgent
2026-01-25 | 2026-01-25 |  |  | 142 |  | Stock out products still receiving orders | Bugsrc | Fail | Rakibul Islam | Functional | Imran |  | Production | Client Urgent
|  |  |  | 143 |  | Subcategory product toggle not reflecting in client site | Bugsrc | Fail |  | Functional | Imran |  | Production | Client Urgent
|  |  |  | 144 |  | Add product-wise logistics | Bugsrc | Not a Bug |  | Functional | Imran |  | Production | Client Urgent
| 2026-01-25 |  |  | 145 |  | Newly added books not searchable |  | Backend/APIs issue | Rakibul Islam, Mir Nayem | Functional | Imran |  | Production | Client Urgent
2026-01-26 | 2026-01-26 |  |  | 146 |  | DC value not reflecting properly |  | Close | Rakibul Islam | Functional | Imran |  | Production | Client Urgent
|  |  |  | 147 |  | Payment done but no sticker | Bugvideo | Fail |  | Functional | Imran |  | Production | Client Urgent
| 2026-01-27 |  |  | 148 |  | bKash SSLCommerz redirect URL not working | Bugsrc | Resolved | Rakibul Islam | Functional | Imran |  | Production | Client Urgent |  |  | Product URL
2026-01-27 | 2026-01-27 |  |  | 149 |  | Recently sold product API loading issue | Bugsrc | Close | Mir Nayem | Functional | Imran |  | Production | Client Urgent |  |  | Bugsrc
| 2026-01-27 |  |  | 150 |  | Subcategory product loading on homepage issue |  | Close | Mir Nayem | Functional | Imran |  | Production | Client Urgent
2026-01-28 |  |  |  | 151 |  | Blog pagination implemented in tech store |  | Fail | Morshedul Islam Munna , Md. Ashikuzzaman | Functional | Imran |  | Production | Client Urgent
|  |  |  | 152 |  | Cashback campaign logic split issue |  | Close | Md. Nazmul Hasan | Functional | Imran |  | Production | Client Urgent
|  |  |  | 153 |  | Sub-subcategory page not found |  | Close | Md. Nazmul Hasan | Functional | Imran |  | Production | Client Urgent
2026-02-02 | 2026-02-09 |  |  | 154 | Voucher | Order confirm modal not closing properly |  | Resolved | Md. Nazmul Hasan | Functional | Imran |  | Production | Client Urgent
2026-02-03 | 2026-02-03 |  |  | 155 |  | Wrong supplier showing | Bugsrc | Resolved | Md. Nazmul Hasan | Functional | Imran |  | Production | Client Urgent
2026-02-07 | 2026-02-07 |  |  | 156 |  | Discount validation issue between COD and bKash | Bugsrc | Close | Rakib Bhai Founder | Functional | Imran |  | Production | Client Urgent
| 2026-02-07 |  |  | 157 |  | Coupon round figure needed in frontend | Bugsrc | Fail | Md. Nazmul Hasan | Functional | Imran |  | Production | Client Urgent |  |  | Book URL
2026-02-09 | 2026-02-09 |  |  | 158 |  | PDF upload resolution issue | Bugsrc | Resolved | Md. Nazmul Hasan | Functional | Imran |  | Production | Client Urgent
| 2026-02-09 |  |  | 159 |  | Order amount mismatch between UI and Excel | Bugsrc | Resolved | Md. Nazmul Hasan | Functional | Imran |  | Production | Client Urgent
|  |  |  | 160 |  | Add to cart popup alignment issue | Product URL | Fail |  | Functional | Imran |  | Production | Client Urgent |  |  | PDF URL
2026-02-14 |  |  |  | 161 |  | Product review missing |  | Fail |  | Functional | Imran |  | Production | Client Urgent
2026-02-16 | 2026-02-17 |  |  | 162 |  | Marketing and flash sale sorting config needed |  | Resolved | Md. Ashikuzzaman | Functional | Imran |  | Production | Client Urgent
2026-02-17 | 2026-02-17 |  |  | 163 |  | Product details alignment updated |  | Resolved | Md. Ashikuzzaman | Functional | Imran |  | Production | Client Urgent
2026-02-17 |  |  |  | 164 |  | New book not appearing in search |  | Need to new feature |  | Functional | Imran |  | Production | Client Urgent
| 2026-02-17 |  |  | 165 |  | PDF resolution issue |  | Resolved | Md. Ashikuzzaman | Functional | Imran |  | Production | Client Urgent
| 2026-02-17 |  |  | 166 |  | Logistics condition issue |  | Resolved | Md. Ashikuzzaman | Functional | Imran |  | Production | Client Urgent
2026-02-22 |  |  |  | 167 |  | Sidebar button click issue in Bimela |  | Fail |  | Functional | Imran |  | Production | Client Urgent
|  |  |  | 168 |  | Category search not working properly | Bugsrc | Fail |  | Functional | Imran |  | Production | Client Urgent |  |  | Book url
| 2026-02-22 |  |  | 169 |  | OTP login should be mandatory for order placement | Bugsrc | Resolved | Mir Nayem | Functional | Imran |  | Production | Client Urgent
2026-02-26 | 2026-02-26 |  |  | 170 |  |  |  | Resolved | Md. Ashikuzzaman | Functional | Imran |  | Production | Client Urgent
| 2026-02-26 |  |  | 171 |  |  |  | Resolved | Mir Nayem | Functional | Imran |  | Production | Client Urgent | Again arise issue
2026-03-06 |  |  |  | 172 |  |  |  | Fail |  | Functional | Imran |  | Production | Client Urgent
[8 empty] | Fail |  | Functional | Imran |  | Production | Client Urgent
[8 empty] | Fail |  | Functional | Imran |  | Production | Client Urgent
[8 empty] | Fail |  | Functional | Imran |  | Production | Client Urgent
[8 empty] | Fail |  | Functional | Imran |  | Production | Client Urgent
[8 empty] | Fail |  | Functional | Imran |  | Production | Client Urgent
[8 empty] | Fail |  | Functional | Imran |  | Production | Client Urgent
[8 empty] | Fail |  | Functional | Imran |  | Production | Client Urgent